## Agile Project Plan (hidden)
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Product Release | Alex B. | 2022-09-02 | 2022-10-10 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  | Alex B. |  | 2022-09-03 | 2022-09-13 | 10 | Complete
| Feature 1 |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | Complete
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | Complete
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-13 | 4 | Overdue
| Sprint 2 |  | Jacob S. |  | 2022-09-16 | 2022-09-24 | 8 | In Progress
| Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | In Progress
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | Not Started
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | Not Started
| Sprint 3 |  | Shari W. |  | 2022-09-25 | 2022-10-05 | 10 | Not Started
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | Not Started
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | Not Started
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Android apps | ammar alabrash | 2020-06-02 | 2020-07-04 |  | 50% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
impact analysis
| map out the functional requirements |  | ammar alabrash | High | 2020-01-04 | 2020-01-18 | 14 | in process
| map out users and functionals |  | hamza abo taym | High | 2020-01-10 | 2020-01-30 | 20 | in process
| issues resolution |  | mahmoud kayal | Low | 2020-01-14 | 2020-01-28 | 14 | not started
design and build
| design databaee |  | osama audi | High | 2020-02-04 | 2020-02-27 | 23 | Done
| write the code of bankend and connect to DB |  | nour alkayal | low | 2020-01-10 | 2020-01-30 | 20 | Done
| write the code of UI for android APP |  | ammar alabrash | High | 2020-01-14 | 2020-01-28 | 14 | not started
testing
| test the backend |  | hamza abo taym | High | 2020-03-10 | 2020-03-28 | 18 | Done
| test the frontend |  | mahmud kayal | medium | 2020-03-13 | 2020-03-29 | 16 | in process
| test the interface to the legacy systems |  | osama audi | High | 2020-03-15 | 2020-03-30 | 15 | not started

## -Disclaimer- (hidden)
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.